## Projects
Project | RAG | Phase | Project lead | Progress | Start date | Estimated end | Next milestone | Obstacles | Notes
North Sea Hub | Green | Delivery | Ada Ng | 72 | 2026-06-11 | 2026-09-19 | FAT complete |  | On track for Q3
Arctic Link | Amber | Delivery | Bo Berg | 45 | 2026-05-12 | 2026-08-30 | Cable pull | Weather window | Watch supplier lead time
Yard Retrofit | Red | Initiation | Cara Diaz | 18 | 2026-07-11 | 2026-08-20 | Scope freeze | Budget overrun | Critical path slip
Digital Twin v2 | On track | Build | Dan Okonkwo | 88 | 2026-04-12 | 2026-08-25 | UAT
HSEQ Pulse | At risk | Operate | Eva Holm | 55 | 2026-01-22 | 2026-08-15 | Audit prep | Missing evidence
Port Expansion | R | Plan | Finn Olsen | 12 | 2026-08-15 | 2027-02-06 | Permits |  | Not started
Crew Roster | G | Operate | Ada Ng | 100 | 2025-07-06 | 2026-07-31 | Closed |  | Complete
Spare Parts AI | Yellow | Build | Bo Berg | 33 | 2026-06-26 | 2026-11-08 | Model v1 | Data quality